## Definizione
Fornitori livello V
Definisce, sviluppa ed installa su un veicolo completo (eventualmente predisposto) sistemi / moduli / componenti finalizzati
a specializzare la missione del veicolo stesso (trasformazione) in coerenza con le specifiche di interfaccia e funzionali
nel rispetto degli obiettivi (tecnici, prestazionali, economici, temporali) assegnati per il perimetro di competenza,
senza degrado / variazione delle prestazioni dei sistemi interfacciati

## Medium-Level RASI
R - Responsabile (incaricato dell'attività)
A-Approvazione (chi può concedere/negare l'approvazione)
S-Sostegno (obbligato a fornire sostegno)
I - da informare
KP1 Fuel Line Damper - FC00SAA78530 ¦ Supplier: Nobel Auto
| Compiti di medio livello | SI Level II |  | Livello SI I |  |  | Livello SI II |  |  | Livello SI III |  |  | Livello SI IV |  |  | Livello SI V
|  | GM | Nobel Auto | Fiat | Liv. 1 | Liv. strategico 2 | Fiat | Liv. 1 | Liv. strategico 2 | Fiat | Liv. 1 | Liv. strategico 2 | Fiat | Liv. 1 | Liv. strategico 2 | Fiat | Liv. 1 | Liv. strategico 2 | NOTE
1 | Design Management (concerning Component/System)
1 | Time schedule planning processing at vehicle level | R | S | R |  |  | R |  |  | R |  |  | R |  |  | R
2 | Time schedule planning processing at system level | A | R | R | S |  | R | S |  | A | R |  | A | R |  | I | R
3 | Time schedule planning processing at module and component level |  |  | R | S | S | A | R | S | A | R | S | A | R |  | I | R
4 | To define targets for Lev. 1 (product cost, design cost, investment) | R |  | R |  |  | R |  |  | R |  |  | R |  |  | R
5 | To define targets for strategic Lev. 2 (product cost, design cost, investment) | R |  | R |  |  | R |  |  | A | R |  | A | R |  | na | na
6 | To define the system / module perimeter | R | S | R |  |  | R |  |  | R |  |  | R |  |  | A | R
7 | To define the system team members (labor and competence of supplier) |  |  | R |  |  | R | S |  | A | R |  | A | R |  |  | R
8 | To define the module and component development team members (labor and competence of supplier) |  |  | R |  |  | A | R |  | A | R |  | A | R |  |  | R
9 | To supervise the activity of suppliers |  |  | R |  |  | R |  |  | R | S |  | R | S |  | I | R
10 | To develop PSI (Integrated Experimental Plan) at system level | R | S | R |  |  | R | S |  | A | R |  | A | R |  | I | R
11 | To develop PSI (Integrated Experimental Plan) at module and component level |  |  | R |  |  | A | R |  | A | R |  | A | R |  | I | R
12 | To process the vehicle development program (Engineering Build Plan) | R | S | R |  |  | R |  |  | R |  |  | R |  |  |  | R
13 | To carry out the MOB (Make or Buy) plan | R | I | R |  |  | R |  |  | R |  |  | R |  |  | R
14 | To define and to manage the interfaces between system and vehicle |  |  | R |  |  | R |  |  | R | S |  | A | R |  | A | R |  | Focus on lay-out
15 | To select and to manage the Lev. 2 suppliers | A | R | R |  |  | R | S |  | A | R |  | A | R |  | I | R
16 | To select and to manage the Lev. 1 suppliers |  |  | R |  |  | R |  |  | R |  |  | R |  |  | R
17 | Lev. 2 component integration into module |  |  | R |  |  | A | R | S | A | R | S | S | R | S |  | R | S
18 | Definition of contract between car maker and Lev. 1 supplierrs |  |  | R |  |  | R |  |  | R |  |  | R |  |  | R | S
19 | Participation of technical staff to training on car maker processes | S | R | S | R |  | S | R |  | S | R |  | S | R |  | na | na
20 | To provide the suppliers with the access to car maker information system | R | S | R |  |  | R |  |  | R |  |  | R |  |  | na
21 | To implement the acces to the car maker information systems | S | R | S | R |  | S | R |  | S | R |  | S | R |  | na | na
22 | To provide all the technical information (at physical and logic levels, including the hardware and software details) necessary for supporting the decision in Design Reviews and Gate Reviews | S | R | R | S | S | A | R | S | A | R | S | A | R | S |  | R | S
23 | - Design progress status at system level: Cost, Weight, Times, Quality |  |  | R |  |  | R | S | S | A | R | S | A | R | S |  | R | S
24 | - Design progress status at module/component level: Cost, Weight, Times, Quality | A | R | R |  |  | A | R | S | A | R | S | A | R | S |  | R | S
25 | - Design progress status: physical tests at system level |  |  | R |  |  | R | S | S | A | R | S | A | R | S |  | R | S
26 | - Design progress status: physical tests at module / component level | A | R | R |  |  | A | R | S | A | R | S | A | R | S |  | R | S
27 | - Design progresss status: virtual simulations on (sub-)systems |  |  | R |  |  | R | S | S | A | R | S | A | R | S |  | R | S
28 | - Design progress status: virtual simulations on module/components | A | R | R |  |  | A | R | S | A | R | S | A | R | S |  | R | S
29 | - Design progress status: process validation at virtual level (at component / module level) | A | R | A | R | S | A | R | S | A | R | S | A | R | S |  | R | S
30 | - Design progress status: process validation (at component / module level) | A | R | A | R | S | A | R | S | A | R | S | A | R | S |  | R | S
31 | To approve Design Review and Gate Review |  |  | R |  |  | R |  |  | R |  |  | R |  |  | A | R
32 | To process the Quality Plan (at component / module level) | A | R | A | R | S | A | R | S | A | R | S | A | R | S | A | R | S
2 | Requirement definition (incl. updating/modifications)
1 | To process the Vehicle Technical Specification (VTS) | R | S | R |  |  | R |  |  | R |  |  | R |  |  | R
2 | To develop and to update the Statement of Requirements (SOR) / Product Sheet (initial, complete , final) | R | S | R |  |  | R |  |  | R |  |  | R |  |  | R (*) |  |  | (*) at vehicle level
3 | To process the Sub-system Technical Specification, SSTS, initial | R | S | R |  |  | R |  |  | R |  |  | R |  |  | na
4 | To process the Sub-system Technical Specification, SSTS, complete - suggestions for improvement | S | R | R |  |  | A | R |  | A | R |  | A | R |  | I | R
5 | To develop and to update the Sub-system Technical Specification, SSTS, final issue | R | S | R |  |  | R | S | S | R | S | S | A | R | S | I | R | S
6 | To develop the definitive Component Technical Specification, CTS, for Lev. 1 / Lev. 2 suppliers |  |  | R |  |  | R | S | S | A | R | S | A | R | S | I | R | S
7 | To define the system failure frequency targets |  |  | R | bar: R R; R A; A A; I I
8 | To define the failure frequency target for module and components |  |  | R | bar: R R; R A to S R; A A to R R; I I to R R
9 | To define the cost targes tin system warranty |  |  | R | bar: R R; R A; A A; I I
10 | To define the cost targets in warranty for module and component suppliers |  |  | R | bar: R R; R A to S R; A A to R R; I I to R R
3 | Concept
1 | To process concept for system architecture |  |  | R | bar: R R; R A; A A to R R; I I to R R
2 | To suggest improvements in system architecture |  |  | R | bar: R R; R A to S R; A A to R R; I I to R R
3 | To process concept for the technical solution at module / component level | S/A | R | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
4 | Comparative assessment of system concepts | S | R | R |  |  | R | S | S | A | R | S | A | R | S | A | R | S
5 | Comparative assessment of Module and Component concepts (including presentation) |  |  | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
6 | To prove the capacity of reaching the main technical targets (at module and component level) |  |  | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
7 | To build and to provide concept prototype | S | R |  | R | bar: R R; R R; R R; R R
4 | Style
1 | To release mathematic models (concerning the style) |  |  | R | bar: A A; A A; A A; I I
2 | To check the technical feasibility of component/ module against the mathematic models (concerning the style) |  |  | R |  |  | A | R | S | A | R | S | A | R | S | A | R | S
3 | To generate the mathematics of module / components | R | S | R | bar: A A to R R; A A to R R; A A to R R; I I to R R
4 | To release the mathematics of module / components | R | S | R | bar: A A to R R; A A to R R; A A to R R; I I to R R
5 | To define the technical specification (grain, color, brightness…) |  |  | R | bar: A A; S S to A A; S S to I I; S S
6 | To approve the component against the technical specification (grain, color, brighteness...) |  |  | R | bar: A A; A A; A A; I I
7 | To define the clearance and profile diagram |  |  | R | bar: A A; A A; A A; I I
5 | Packaging
1 | To develop architecture and packaging at vehicle level | R | S | R | bar: A A; A A to R R; A A to R R; I I to R R
2 | To process and to update the geometric data for DMU and PMU | I | R | R |  |  | A | R | S | A | R | S | A | R | S | S | R
3 | To issue the geometric data for DMU |  |  | R |  |  | R | S | S | A | R | S | A | R | S | S | R
4 | To process and to update DMU | R | S | R | [14 empty] | At vehicle level | bar: A A; A A; A A; I I
6 | Product Development: Design
1 | To define the components with safety contents (with characteristics to be checked) | R | S | R | bar: A A; A A; A A; I I to R R
2 | To define the technical design and to release drawings according to the format and design standards defined by the car maker | A | R | R |  |  | A | R | S | A | R | S | A | R | S |  | R (*) | S | (*) For lev. V, format to be agreed between FGA and defined supplier
3 | To ensure the correct PHYSICAL interfaces among all the module components and between the module and the other system components |  |  | R |  |  | A | R | S | A | R | S | A | R | S | A | R | S
4 | Managing of Modification Order (ODM) and variations, including the follow up | A | R | R |  |  | R | S | S | A | R | S | A | R | S | R | S | S
5 | To check drawings and data | A | R | R |  |  | R | S | S | R | S | S | R | S | S | I | R | S
6 | To carry out the dimension managing (check of tolerance series) at vehicle level | R | S | R |  |  | R | S | S | R | S | S | A | R | S | S | R | S
6b | To carry out the dimension managing (check of tolerance series) at module / components level | R | S | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
7 | To process KPC - Key product characteristics | A | R | R |  |  | A: R; A: A; R: R; A: A; R: R; I: I; R: R
8 | To process the prototype component list | A | R | R | bar: A to S
9 | To process CODEP / BOM (*) | A | R | R |  |  | R | S | S | A | R | S | A | R | S | I | R(*) | S(*) | (*)Only BOM =( Bill of Materials) managed by supplier including Weight
10 | To carry out the application FMEA |  |  | R |  |  | R | S | S | R | S | S | A | R | S | I | R | S
11 | To carry out the Design FMEA at system level and the Fault Tree Analysis | A | R | R |  |  | R | S | S | A | R | S | A | R | S | I | R | S
12 | To carry out the Design FMEA at MODULE and component level |  |  | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
13 | To carry out the design analysis concerning the installation/assembling at Factory (at vehicle level) | R | S | R |  |  | R | A | S | R | A | S | A | R | S | na | na | na
13b | To carry out the design analysis concerning the installation/assembling at Factory (at module / component level) | R | S | R |  |  | A | R | S | A | R | S | A | R | S | na | na | na
14 | To design and to carry out components and specific accessory tools necessary for ensuring serviceability | A | R | A | R | S | A | R | S | A | R | S | A | R | S | A | R | S
7 | Product development: simulation
1 | To provide all the model/ results of simulations necessary for carrying out the virtual analysis at system / vehicle level |  |  | A | R | S | A | R | S | A | R | S | A | R | S | A | R | S
2 | To carry out the product simulation and the performance analysis at system level | S/A | R | R |  |  | R | S | S | A | R | S | A | R | S | I | R | S
3 | To carry out the product simulation and the performance analysis at module and component level |  |  | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
4 | To carry out the virtual (integrative) analysis at vehicle level | R | S | R | bar: R A to S S
5 | To carry out the virtual analysis of process at vehicle level | R | S | R | bar: R A to S S
8 | Product development - Experimentation and release at component / system level
1 | To produce and to provide components or assemblies for prototypes | A | R |  | R | S | bar: S R to S S; R R to S S; R R to S S; R R to S S
2 | To build prototype vehicles | R | S | R |  |  | R A: R; A A: R; A A: R; R R: R (*) | (*) For Supplier perimeter
3 | To produce and to provide parts or assies to update the prototype for all the activities of car maker, on request | S | R |  | R | S | bar: S R to S S; R R to S S; R R to S S; R R to S S
4 | To produce and to provide, within 1 day, the spare parts or assies for faulty prototypes, for all the internal activities of the car maker, on request | S | R |  | R | S | bar: S R to S S; R R to S S; R R to S S; R R to S S
5 | To update the prototypes for all the internal activities of the car maker | R | S | R |  |  | R | S | S | R | S | S | A | R | S |  | R | S
6 | To define and to ask the hardware required foexperimentation of components and MODULE (structural parts, vehicles, etc.) | S | R | R |  |  | R | S | S | A | R | S | A | R | S |  | R | S
7 | To define, to plan and to carry out, for vehicle and system, the bench tests of competence of car maker (in addition to the activity of the supplier) for development and release and to prepare reports |  |  | R | bar: R A to S S
8 | To define, to plan and to carry out all the bench and vehicle tests for development and release of components and MODULE and to prepare reports | A | R | A | R | S | A | R | S | A | R | S | A | R | S | A | R | S
9 | To carry out the release tests of vehicle inside (integrative) | R | S | R | bar: R A to S S
10 | Report on development status at system level | A | R | R |  |  | R | S | S | A | R | S | A | R | S | A | R | S
11 | Report on development status at module and component level |  |  | R |  |  | A | R | S | A | R | S | A | R | S | A | R | S
12 | To carry out the design failure analysis of system/components, due to deviations (non-conformities) from the Sub-system Technical Specification (identification of causes) |  |  | R | bar: R A to S S
12b | To carry out the design failure analysis of system/components, due to deviations (non-conformities) from CTS (identification of causes) |  |  | R |  |  | R | S | S | A | R | S | A | R | S | I | R | S
13 | To define the actions to be carried out on system to remove faults |  |  | R |  |  | R | S | S | A | R | S | A | R | S | I | R | S
14 | To define the actions to be carried out on module and components to remove faults |  |  | R |  |  | A | R | S | A | R | S | A | R | S | I | R | S
15 | Approval of Equipment Release / Technical Release of system, module and components |  |  | R | bar: R R A to S S S
9 | Integration (FUNCTIONAL and LOGIC, NOT PHYSICAL)
1 | System integration on vehicle | R | S | R | S | S | R | S | S | R | S | S | R | S | S | A | R | S
2 | Integration among different systems |  |  | R | S | S | bar: R R A to S S S
3 | Integration of modules and components in the system |  |  | R | S | S | R | S | S | A | R | S | A | R | S | I | R | S
4 | Coordination with other functional areas at the car maker | S | R | bar: R to S
10 | Production and launch process
1 | To input problems to SITRA (Fault Tracking Integrated System) | A | R | bar: R; R; A; A; I
2 | To identify the solutions to solve the problems referred to SITRA at system level |  |  | R | S | S | R | S | S | A | R | S | A | R | S | A | R | S
3 | To identify the solutions to solve the problems referred to SITRA at MODULE and COMPONENT level |  |  | R | S | S | A | R | S | A | R | S | A | R | S | A | R | S
4 | Production process, including the tools produced by the supplier (components/module) | A | R | bar: R to S
5 | Car maker process FMEA |  |  | R | S | S | R | S | S | R | S | S | R | S | S | R(*) | S | S | (*) Only for modification made by carmaker
6 | Module/component process FMEA |  |  | A | R | R | A | R | R | A | R | R | A | R | R | I/A(*) | R | R | (*) Approval only for module/components installation on vehicle
7 | To define KCC (Key Control Caracteristics) and Process Control Plan (at component and MODULE level) | A | R | A | R | R | A | R | R | A | R | R | A | R | R | A(*) | R | R | (*) For SI V supplier to define KCC
8 | To define the packing and transport requirements | A | R | R | S |  | R | S |  | R | S |  | R | S |  | R(*) | R |  | (*) for complete vehicle
9 | To prepare the Transport Plan | R | S | R | S |  | R | S |  | R | S |  | R | S |  | R(*) | R |  | (*) for complete vehicle
10 | Checks of Process / Pre-series at Pilot Factory and Production Factory | R | S | R | S |  | R | S |  | R | S |  | R | S |  | A | R
11 | To define the test plan for the component qualification (process validation) |  |  | R | S | S | A | R | R | A | R | R | A | R | R | A | R | R
12 | To carry out the component qualification | A | R | bar: R to S
13 | Active support for press vehicle launch, including component updating on request | S | R | bar: R to S; R to S; A to R; A to R; I to R
14 | To carry out the vehicle tests for component qualification | bar: R to S
15 | Qualification report approval | bar: R to S
16 | Component reliability plan |  |  | R | S | S | A | R | R | A | R | R | A | R | R | A | R | R
17 | To carry out the component reliability tests | bar: R to S
18 | To carry out the vehicle reliability tests | bar: R to S
19 | Component test approval and report for law provisions | bar: R to S
20 | Vehicle test approval and reports for law provisions | bar: R to S
21 | To define the manufacturing standard for car maker systems | bar: R to S
22 | To define the manufacturing standard for the module |  |  |  | R | S |  | R | S |  | R | S |  | R | S | A | R | S
23 | To identify the components with report characteristics |  |  | R | S | S | R | S | S | R | S | S | R | S | S | A (*) | R | S | (*) For SI V supplier to define Report Characteristics
24 | To define the control and capability plan for the car maker process |  |  | R: R; R: R; A: R; A: R; I: R(*); R: R(**) | (*) Only for modification made by carmaker (**) Complete vehicle after module/components installation
25 | To define the control and capability plan for the Lev. 2 component supplier |  |  | A | S | R | A | S | R | A | S | R | A | S | R | A | S | R
26 | To define the control and capability plan for the Lev. 1 supplier | bar: R to S; R to S; A to R; A to R; I to R
27 | To define the components subject to traceability | bar: R; R; A; A; I
28 | To ensure the traceability of module / components |  |  | A | R | S | A | R | S | A | R | S | A | R | S | A | R | S
29 | To plan the vehicle production increase | bar: R; R; A; A; I to R
30 | To plan the module / component production increase |  |  | A | R | S | A | R | S | A | R | S | A | R | S | I | R | S
31 | To define the equipment level of the installation line for module / components |  |  | A | R | S | A | R | S | A | R | S | A | R | S | I | R | S
32 | To prepare the equipment for the installation line of module / components |  |  | A | R | S | A | R | S | A | R | S | A | R | S | I | R | S
33 | To carry out the process check tests according to the module / component control plan | bar: R A A A to R S S S
34 | To carry out the process check tests according to the vehicle control plan | bar: R A A A; R A A A; R A A A; R A A A; A I I I
35 | To check the compliance between process parameters and capability defined for the module/component | bar: R A A A to R S S S
36 | To check the compliance between process parameters and capability defined for the vehicle | bar: R A A A; R A A A; R A A A; R A A A; A I I I
37 | To inform the car maker of any deviation between process parameters and capability defined for module/components |  |  | A | R | S | A | R | S | A | R | S | A | R | S | A | R | S
38 | To certify the module / components supply to final customer |  |  | A | R | S | A | R | S | A | R | S | A | R | S | I | R | S
39 | To certify the supply of Lev. 2 components to final customer |  |  | A | I | R | A | I | R | A | I | R | A | I | R | I | A | R
40 | To identify quality process problems for module/components and perform diagnosis and corrective actions | bar: A to S
41 | To define the logistic system for module / components (flows and stocks) |  |  | R | S |  | R | S |  | R | S |  | R | S |  | I | R
42 | To define the logistic system for the Lev. 2 components |  |  | I | R | S | I | R | S | I | R | S | I | R | S | I | R | S
43 | To manage the logistic performances of Lev. 2 suppliers |  |  | A | R |  | A | R |  | A | R |  | A | R |  | I | R
44 | To manage the logistic performances of Lev. 1 suppliers |  |  | A: R; A: R; A: R; A: R; I: R(*) | (*) Only for complete car release
45 | To assemble the module |  |  | R: R; R: R; R: R; R: R; R: R(*) | (*) Including safety procedures for GAS filling ( for LPG/CNG ) and end of line test
46 | To ensure the module installation conformity |  |  | A | R | S | A | R | S | A | R | S | A | R | S | I | R | S
47 | To carry out tests and checks on module / components of Lev. 2 / components of Lev. 1 |  |  | A | R | S | A | R | S | A | R | S | A | R | S | I | R | S
48 | To define the management of rejectconcerning the module |  |  | R | S | S | R | S | S | R | S | S | R | S | S | I | R | S
49 | To define the specifications for the servicing at line in car maker factories |  |  | R | S | S | R | S | S | R | S | S | R | S | S | NA | NA | NA
50 | To ensure the servicing at line in car maker factories | bar: R R R; R R R; R R R; R R R; R I I to R(*) S S
11 | Continuous improvement and service up to model prodution end
1 | To provide data for workshop manuals and software included in updating | A | R | A | R | R | A | R | R | A | R | R | A | R | R | A | R(*) | R | (*) Included in field service driven by specific contract
2 | Preparation of LUM (use and maintenance manual) | R | S | bar: A A to R(*) S S
3 | Analysis of problems concerning quality (warranty, recall campaign, etc.) | bar: A A to R(*) S S
4 | Action of restraint and solution of quality problems concerning the module /component design |  |  | R | S | S | A | R | S | A | R | S | A | R | S | A | R | S
5 | Action of restraint and solution of quality problems concerning the module / component process | A | R | bar: A A to R(*) S S
6 | Modification and issue of design after SOP | A | R | R | S | S | A | R | S | A | R | S | A | R | S | A | R | S
7 | Ricycling: to prepare information for disassembly. To analyse the content of materials | A | R | bar: A A to R(*) S S
8 | To provide information on materials on IMDS | I | R | bar: A A to R(*) S S
9 | To provide the check-list for the system diagnosis in network (at dealers/workshops) | bar: A A; R A A; R A A to R R R; R A A to R R R; R I I to R(*) R R
10 | To provide the check-list for the module / component diagnosis in network (at dealers/workshops) |  |  | R | S |  | A | R |  | A | R |  | A | R |  | A | R
11 | To define the warranty cost management system | bar: A A to R(*) S S
12 | To carry out the diagnosis on system at the network (dealers, workshops, etc.) for critical cases not identified by standard diagnostic instrumentation | bar: A A; R A A; R A A to R R R; R A A to R R R; R I I to R(*) R R
13 | To carry out the diagnosis on module/components at the network (dealers, workshops, etc.) for critical cases not identified by standard diagnostic instrumentation |  |  | R | S |  | A | R |  | A | R |  | A | R |  | A | R
12 | Product Cost Management
1 | Value analysis: to provide all the technical information (at physical and logic level, including hardware and software details) necessary for support the car maker assessment | S | R | R | S |  | A | R | S | A | R | S | A | R | S | A | R | S
2 | System cost reduction analysis |  |  | R | S | S | R | S | S | A | R | S | A | R | S | A | R | S
3 | Module / component cost reduction analysis |  |  | R | S | S | A | R | S | A | R | S | A | R | S | A | R | S
4 | Research of proposal for the system cost reduction |  |  | R | S | S | R | S | S | A | R | S | A | R | S | A | R | S
5 | Research of proposal for the module / component cost reduction |  |  | R | S | S | A | R | S | A | R | S | A | R | S | A | R | S
6 | To approve the proposed modification | bar: A A; R A A; R A A; R A A; R I I
7 | To negotiate and to define the price for Lev. 1 module / component | bar: A A; R A A; R A A; R A A; R I I
7 | To negotiate and to define the price for Lev. 2 module / component | bar: A A; R A A; R A A to R R R; R A A to R R R; R I I to R(*) R R
8 | To define the system cost breakdown and to update it |  |  | R | S | S | R | S | S | A | R | S | A | R | S | A | R | S
9 | To define the module / component cost breakdown and to update it |  |  | R | S | S | A | R | S | A | R | S | A | R | S | A | R | S