AI-AUGMENTED APQP

30-Day Pilot Commitment Plan

26 February – 27 March 2026  |  Confidential – Team Only

TARGET by Day 30:

Pilot A committed (LOI signed or verbal + date).  Pilot B committed.  Pilot C and D showing strong, informed interest.

HOW TO USE THIS DOCUMENT:

Section 1 is the timeline overview — read this first to understand the shape of the plan.

Section 2 is the daily task list — each person finds their own rows by Owner column. Update the Status column as tasks are completed.

COLOUR CODE:

|  | Team Kickoff / full-team event |
| --- | --- |
|  | Pilot meeting (C leads solo) |
|  | On-site commitment meeting (full team) |

## Section 1 — Timeline Overview

| WD | Date | Key Event / Milestone | Phase |
| --- | --- | --- | --- |
| WD1 | Thu 26 Feb | TEAM KICKOFF — align plan, roles, boundaries | 1 |
| WD2 | Fri 27 Feb | Prep sprint starts: service offer, demo, pilot spec | 1 |
| WD3 | Mon 2 Mar | C meets Pilot C (1st personal meeting) | 1 |
| WD4–5 | Tue–Wed 3–4 Mar | Confidence materials ready for review | 1 |
| WD6 | Thu 5 Mar | Full team dry-run of Day 10 talking points | 1 |
| WD7 | Fri 6 Mar | Final polish; C sends personal note to Pilot A & B | 1 |
| WD8 | Mon 9 Mar | C meets Pilot A & B (2nd meeting — listening mode) | 2 |
| WD8 | Mon 9 Mar | C debriefs team; B compares Pilot A vs B objections | 2 |
| WD9–11 | Tue 10 – Thu 12 Mar | Build commitment meeting materials from debrief | 2 |
| WD12 | Fri 13 Mar | Full team dry-run of on-site commitment meeting | 2 |
| WD13 | Mon 16 Mar | Confirm on-site dates & attendees with Pilot A & B | 2 |
| WD14 | Tue 17 Mar | C meets Pilot D (1st personal meeting) | 2 |
| WD15–16 | Wed–Thu 18–19 Mar | Final material refinement; logistics confirmed | 3 |
| WD17–18 | Fri–Mon 20–23 Mar | On-site commitment meetings: Pilot A then Pilot B | 3 |
| WD19–22 | Tue 24 – Fri 27 Mar | Follow-up, LOI close, Day 30 target achieved | 3 |

Section 2 — Daily Task List

Each person: find your rows by the Owner column. Mark Status column when complete. C updates after every pilot meeting.

| WD | Date | Owner | Task | Support | Status ✓ |
| --- | --- | --- | --- | --- | --- |
| PHASE 1 — Foundation & Confidence Materials (WD1–WD7) |  |  |  |  |  |
| WD1 | Thu 26 Feb | ALL | TEAM KICKOFF (60–90 min). Agree on: this plan, role boundaries, D's conflict-of-interest limits at Pilot A, definition of Day 30 success. C presents Pilot A & B debrief — exact words, hesitations, AI questions raised. | — |  |
| WD1 | Thu 26 Feb | C | After kickoff: write up Pilot A & B debrief notes in shared format for team reference. | — |  |
| WD1 | Thu 26 Feb | B | Start service offer draft: scope, deliverables, one price (not a range), pilot terms, what success looks like, customer time commitment. | C reviews |  |
| WD1 | Thu 26 Feb | A | Start demo concept: AI-assisted FMEA walkthrough for a generic fuel system component. Plausible, not polished. Focus on showing the process, not a finished product. | D validates realism |  |
| WD1 | Thu 26 Feb | D | Start pilot operational spec: what we need from pilot (named program, document access, one internal contact), what we deliver, timeframe. Separate versions for Pilot A and Pilot B. | C reviews |  |
| WD2 | Fri 27 Feb | B+C | Review service offer draft together. C pressure-tests each line as Pilot A CEO, then as Pilot B owner. Simplify anything that raises confusion. | — |  |
| WD2 | Fri 27 Feb | A+D | Sync on demo scenario. D plays sceptical quality manager — does the AI output pass a basic credibility test? Adjust if not. | — |  |
| WD2 | Fri 27 Feb | D | Write D's conflict-of-interest boundary doc (internal only): what D can and cannot do commercially regarding Pilot A. Must be clear before on-site team meeting. | C reviews |  |
| WD3 | Mon 2 Mar | C | PILOT C — 1st personal meeting (solo). Listen-and-build-trust mode. Angle: relief from APQP burden + Jan 2027 FMEA compliance deadline (Pilot C has poor APQP discipline). Capture: specific pain points, AI reaction, language that resonated. | — |  |
| WD3 | Mon 2 Mar | C | Same-day debrief to team: Pilot C pain points, AI reaction, exact phrases used. This feeds the demo and service offer framing. | — |  |
| WD3 | Mon 2 Mar | A | Continue demo build. Incorporate any fuel systems process detail D provided. | D |  |
| WD4 | Tue 3 Mar | A | Complete demo — laptop-ready. Must run without technical issues. If either Pilot A or B asks 'can you show me something?' in WD8 meeting, this is the answer. | D final check |  |
| WD4 | Tue 3 Mar | B | Finalize service offer. Print-ready. Separate versions for Pilot A and Pilot B if scope or pricing differs. | — |  |
| WD4 | Tue 3 Mar | D | Complete pilot operational spec — both Pilot A and B versions finalized. | C |  |
| WD5 | Wed 4 Mar | A | Write plain-language AI explainer (max 2 paragraphs): what AI can and cannot do in APQP. Addresses likely misconceptions: 'just ChatGPT,' 'replaces engineers,' 'needs perfect data.' This is C's reference for WD8. | — |  |
| WD5 | Wed 4 Mar | B | Prepare pricing rationale: why the pilot price is what it is, what customer gets for that, how it compares to cost of current APQP inefficiency. | — |  |
| WD5 | Wed 4 Mar | C | Prepare WD8 meeting approach: 3 open questions to draw out Pilot A and B research findings. Do NOT prepare a new pitch. Prepare to listen and respond. | — |  |
| WD6 | Thu 5 Mar | ALL | Full team sync (60 min): review all materials — demo, service offer, pilot spec, AI explainer, pricing rationale, C's WD8 meeting questions. Identify gaps. Assign any remaining work. | — |  |
| WD6 | Thu 5 Mar | C | Review D's notes on Pilot A internal situation: any program timing that makes a pilot more or less urgent right now. | D |  |
| WD7 | Fri 6 Mar | ALL | No new material. Refinement only. Confirm everything is ready. | — |  |
| WD7 | Fri 6 Mar | C | Send personal note to Pilot A CEO and Pilot B owner (separately, same evening). Not a pitch. Confirm meeting, express genuine interest in hearing how their thinking has developed. | B drafts, C personalises |  |
| PHASE 2 — Second Meetings & Commitment Material Build (WD8–WD16) |  |  |  |  |  |
| WD8 | Mon 9 Mar | C | PILOT A — 2nd personal meeting (solo). 80% listening. Draw out: what did they research, what concerned them, what would build enough confidence to commit to a pilot. Note any program names or timing mentioned. | — |  |
| WD8 | Mon 9 Mar | C | PILOT B — 2nd personal meeting (solo, same day or next morning). Same approach as Pilot A. | — |  |
| WD8 | Mon 9 Mar | C+B | Same-day debrief (C + B). Compare Pilot A and Pilot B: common objections vs. pilot-specific ones. Agree on what the on-site commitment meeting must address for each. | — |  |
| WD9 | Tue 10 Mar | ALL | Full team sync — review WD8 debrief. Agree on commitment meeting agenda for each pilot. Assign prep tasks with WD deadlines. | — |  |
| WD9 | Tue 10 Mar | A | If either CEO raised data security, AI explainability, or tool reliability: prepare specific, honest answers. If demo upgrade needed for a multi-person room, start now. | D |  |
| WD9 | Tue 10 Mar | B | Draft LOI template and pilot agreement outline. Not a full legal document — enough structure that signing feels concrete and manageable. | C reviews |  |
| WD9 | Tue 10 Mar | D | Prepare on-site meeting flow: who presents what, in what order. D: APQP domain questions. A: AI questions. B: commercial questions. C: relationship and overall framing. Max 90 minutes. | C approves |  |
| WD10–11 | Wed–Thu 11–12 Mar | A | Demo upgrade if needed. Ensure it runs smoothly for a room of 3–5 people, not just a laptop conversation. | D |  |
| WD10–11 | Wed–Thu 11–12 Mar | B | Finalize LOI template and pilot agreement. One version per pilot. | — |  |
| WD10–11 | Wed–Thu 11–12 Mar | C | Stay in light contact with Pilot A and B CEOs — available for questions, not pushing. Same-day response if they reach out. | — |  |
| WD12 | Fri 13 Mar | ALL | Full team dry-run of on-site commitment meeting (90 min). D plays Pilot A quality manager with hard APQP questions. B plays sceptical CFO on cost and risk. A must explain AI capability without jargon in under 3 minutes. C manages the room. | — |  |
| WD13 | Mon 16 Mar | C | Confirm on-site meeting dates and who from pilot side will be in the room. Target: Pilot A on WD17, Pilot B on WD18 (or reverse). Agree attendees. | — |  |
| WD14 | Tue 17 Mar | C | PILOT D — 1st personal meeting (solo). Same approach as Pilot C: listen, build trust, uplift and compliance story (poor APQP discipline). Capture pain points and AI reaction. | — |  |
| WD14 | Tue 17 Mar | C | Same-day debrief to team: Pilot D findings. | — |  |
| WD15–16 | Wed–Thu 18–19 Mar | ALL | Final material refinement only — nothing new after WD16. Confirm logistics: travel, venue, equipment, who brings what. | — |  |
| WD15–16 | Wed–Thu 18–19 Mar | C | Send each CEO a brief preview of the on-site meeting — not a full agenda, just enough that they know what to expect and can invite the right people internally. | B drafts |  |
| WD15–16 | Wed–Thu 18–19 Mar | D | Confirm conflict-of-interest boundary is documented and understood by all before entering Pilot A facility. Confirm D's introduction and role in that room. | C |  |
| PHASE 3 — On-Site Commitment Meetings & Close (WD17–WD22) |  |  |  |  |  |
| WD17 | Fri 20 Mar | ALL | ON-SITE: PILOT A. Full team present. Goal: leave with signed LOI or firm verbal commitment + LOI date. D's role in this room must be pre-agreed (domain expert, not internal advocate). | — |  |
| WD18 | Mon 23 Mar | ALL | ON-SITE: PILOT B. Full team present. Same goal: signed LOI or firm verbal + date. | — |  |
| WD18 | Mon 23 Mar | ALL | Post-visit debrief: what worked, what to improve for Pilot C and D engagement. | — |  |
| WD19–22 | Tue 24 – Fri 27 Mar | C+B | Resolve any outstanding LOI items. Written confirmation from both pilots. Day 30 target: Pilot A committed, Pilot B committed, Pilot C and D showing strong and informed interest. | A+D on standby |  |

Last updated: 26 Feb 2026  |  Next review: after WD8 pilot meetings