## 30-Day Tracker
APQP-SA7 · 30-Day Pilot Commitment Plan · WD1 Thu 26 Feb → WD22 Fri 27 Mar 2026
Day 30 Target: Pilot A + B — LOI or firm commitment · Pilot C + D — Strong informed interest, first meeting done
⚑ KEY FLAGS: D at Pilot A on-site (WD17) — role pre-agreed by WD15, domain expert only, not internal advocate. ¦ Pilot C & D pitch angle — burden relief + Jan 2027 FMEA compliance, NOT optimisation. ¦ WD8 blocker rule — clear blocker → full team same day, don't wait for WD9.
WD | Date | Owner | Task | Support | Status | Deliverable Link | Remarks
PHASE 1 — Foundation & Confidence Materials
WD1 | Thu 26 Feb | ALL | 🟡 团队启动会议（60-90分钟）。达成共识：本计划、角色界限、D在试点项目A中的利益冲突限制、第30天成功的定义。C汇报试点项目A和B的进展情况——包括原文、顾虑以及提出的AI相关问题。 | — | Open
WD1 | Thu 26 Feb | C | After kickoff: write up Pilot A & B debrief notes in shared format for team reference. | — | Open
WD1 | Thu 26 Feb | B | Start service offer draft: scope, deliverables, one price (not a range), pilot terms, what success looks like, customer time commitment. | C reviews | Open
WD1 | Thu 26 Feb | A | Start demo concept: AI-assisted FMEA walkthrough for a generic fuel system component. Plausible, not polished. Focus on showing the process, not a finished product. | D validates realism | Open
WD1 | Thu 26 Feb | D | Start pilot operational spec: what we need from pilot (named program, doc access, one internal contact), what we deliver back, timeframe. Separate versions for Pilot A and Pilot B. | C reviews | Open
WD2 | Fri 27 Feb | B+C | Review service offer draft together. C pressure-tests each line as Pilot A CEO, then as Pilot B owner. Simplify anything that raises confusion. | — | Open
WD2 | Fri 27 Feb | A+D | Sync on demo scenario. D plays sceptical quality manager — does the AI output pass a basic credibility test? Adjust if not. | — | Open
WD2 | Fri 27 Feb | D | Write D's conflict-of-interest boundary doc (internal only): what D can and cannot do commercially regarding Pilot A. Must be clean before on-site team meeting. | C reviews | Open
WD3 | Mon 2 Mar | C | 🔵 PILOT C — 1st personal meeting (solo). Listen-and-build-trust mode. Angle: relief from APQP burden + Jan 2027 FMEA compliance deadline. Capture: specific pain points, AI reaction, language that resonated. | — | Open
WD3 | Mon 2 Mar | C | Same-day debrief to team: Pilot C pain points, AI reaction, exact phrases used. | — | Open
WD3 | Mon 2 Mar | A | Continue demo build. Incorporate any fuel systems process detail D provided. | D | Open
WD4 | Tue 3 Mar | A | Complete demo — laptop-ready. Must run without technical issues. Ready if Pilot A or B asks 'can you show me something?' in WD8 meeting. | D final check | Open
WD4 | Tue 3 Mar | B | Finalize service offer. Print-ready. Separate versions for Pilot A and Pilot B if scope or pricing differs. | — | Open
WD4 | Tue 3 Mar | D | Complete pilot operational spec — both Pilot A and B versions finalized. | C | Open
WD5 | Wed 4 Mar | A | Write plain-language AI explainer (max 2 paragraphs): what AI can and cannot do in APQP. Addresses misconceptions: 'just ChatGPT,' 'replaces engineers,' 'needs perfect data.' C's reference for WD8. | — | Open
WD5 | Wed 4 Mar | B | Prepare pricing rationale: why the pilot price is what it is, what customer gets for that, how it compares to cost of current APQP inefficiency. | — | Open
WD5 | Wed 4 Mar | C | Prepare WD8 meeting approach: 3 open questions to draw out Pilot A and B research findings. Do NOT prepare a new pitch. Prepare to listen and respond. | — | Open
WD6 | Thu 5 Mar | ALL | 🟡 Full team sync (60 min): review all materials — demo, service offer, pilot spec, AI explainer, pricing rationale, C's WD8 questions. Identify gaps. Assign remaining work. | — | Open
WD6 | Thu 5 Mar | C | Review D's notes on Pilot A internal situation: any program timing that makes a pilot more or less urgent right now. | D | Open
WD7 | Fri 6 Mar | ALL | No new material. Refinement only. Confirm everything is ready. | — | Open
WD7 | Fri 6 Mar | C | Send personal note to Pilot A CEO and Pilot B owner (separately, same evening). Not a pitch. Confirm meeting, express genuine interest in hearing how their thinking has developed. | B drafts, C personalises | Open
PHASE 2 — Second Meetings & Commitment Material Build
WD8 | Mon 9 Mar | C | 🔵 PILOT A — 2nd personal meeting (solo). 80% listening. Draw out: what did they research, what concerned them, what would build enough confidence to commit. Note any program names or timing mentioned. | — | Open
WD8 | Mon 9 Mar | C | 🔵 PILOT B — 2nd personal meeting (solo). Same approach as Pilot A. | — | Open
WD8 | Mon 9 Mar | C+B | Same-day debrief. Compare Pilot A and Pilot B: common objections vs. pilot-specific ones. Agree on what the on-site commitment meeting must address for each. | — | Open
WD9 | Tue 10 Mar | ALL | 🟡 Full team sync — review WD8 debrief. Agree on commitment meeting agenda for each pilot. Assign prep tasks with WD deadlines. | — | Open
WD9 | Tue 10 Mar | A | If either CEO raised data security, AI explainability, or tool reliability: prepare specific, honest answers. If demo upgrade needed for a multi-person room, start now. | D | Open
WD9 | Tue 10 Mar | B | Draft LOI template and pilot agreement outline. Not a full legal document — enough structure that signing feels concrete and manageable. | C reviews | Open
WD9 | Tue 10 Mar | D | Prepare on-site meeting flow: who presents what, in what order. D: APQP questions. A: AI questions. B: commercial. C: relationship and framing. Max 90 minutes. | C approves | Open
WD10–11 | Wed–Thu 11–12 Mar | A | Demo upgrade if needed. Ensure it runs smoothly for a room of 3–5 people. | D | Open
WD10–11 | Wed–Thu 11–12 Mar | B | Finalize LOI template and pilot agreement. One version per pilot. | — | Open
WD10–11 | Wed–Thu 11–12 Mar | C | Stay in light contact with Pilot A and B — available for questions, not pushing. Same-day response if they reach out. | — | Open
WD12 | Fri 13 Mar | ALL | 🟡 Full team dry-run of on-site commitment meeting (90 min). D plays Pilot A quality manager with hard APQP questions. B plays sceptical CFO. A explains AI without jargon in under 3 minutes. C manages the room. | — | Open
WD13 | Mon 16 Mar | C | Confirm on-site meeting dates and who from pilot side will be in the room. Target: Pilot A on WD17, Pilot B on WD18 (or reverse). Agree attendees. | — | Open
WD14 | Tue 17 Mar | C | 🔵 PILOT D — 1st personal meeting (solo). Listen, build trust, uplift and compliance story (poor APQP discipline). Capture pain points and AI reaction. | — | Open
WD14 | Tue 17 Mar | C | Same-day debrief to team: Pilot D findings. | — | Open
WD15–16 | Wed–Thu 18–19 Mar | ALL | Final material refinement only — nothing new after WD16. Confirm logistics: travel, venue, equipment, who brings what. | — | Open
WD15–16 | Wed–Thu 18–19 Mar | C | Send each CEO a brief preview of the on-site meeting — not a full agenda, just enough that they know what to expect and can invite the right people internally. | B drafts | Open
WD15–16 | Wed–Thu 18–19 Mar | D | Confirm conflict-of-interest boundary is documented and understood by all before entering Pilot A facility. Confirm D's introduction and role in that room. | C | Open
PHASE 3 — On-Site Commitment Meetings & Close
WD17 | Fri 20 Mar | ALL | 🟢 ON-SITE: PILOT A. Full team present. Goal: leave with signed LOI or firm verbal commitment + LOI date. D's role pre-agreed — domain expert, not internal advocate. | — | Open
WD18 | Mon 23 Mar | ALL | 🟢 ON-SITE: PILOT B. Full team present. Same goal: signed LOI or firm verbal + date. | — | Open
WD18 | Mon 23 Mar | ALL | Post-visit debrief: what worked, what to improve for Pilot C and D engagement. | — | Open
WD19–22 | Tue 24 – Fri 27 Mar | C+B | Resolve any outstanding LOI items. Written confirmation from both pilots. | A+D on standby | Open
WD19–22 | Tue 24 – Fri 27 Mar | ALL | Day 30 check: Pilot A committed ✓ Pilot B committed ✓ Pilot C strong interest ✓ Pilot D strong interest ✓ | — | Open

## Overview
APQP-SA7 · Timeline Overview & Day 30 Targets
🎯 DAY 30 TARGETS — 27 Mar 2026
Pilot A | LOI signed or firm verbal commitment with date
Pilot B | LOI signed or firm verbal commitment with date
Pilot C | Strong, informed interest. First personal meeting done.
Pilot D | Strong, informed interest. First personal meeting done.
📅 TIMELINE OVERVIEW
WD | Date | Key Event / Milestone | Phase
WD1 | Thu 26 Feb | 🟡 TEAM KICKOFF — align plan, roles, boundaries |  | Phase 1
WD2 | Fri 27 Feb | Prep sprint: service offer, demo, pilot spec |  | Phase 1
WD3 | Mon 2 Mar | 🔵 C meets Pilot C — 1st personal meeting |  | Phase 1
WD4–5 | Tue–Wed 3–4 Mar | Confidence materials ready for review |  | Phase 1
WD6 | Thu 5 Mar | 🟡 Full team dry-run of WD8 talking points |  | Phase 1
WD7 | Fri 6 Mar | Final polish · C sends personal note to Pilot A & B |  | Phase 1
WD8 | Mon 9 Mar | 🔵 C meets Pilot A & B — 2nd meetings (listening mode) + debrief |  | Phase 2
WD9–11 | Tue 10 – Thu 12 Mar | Build commitment meeting materials from WD8 debrief |  | Phase 2
WD12 | Fri 13 Mar | 🟡 Full team dry-run of on-site commitment meeting |  | Phase 2
WD13 | Mon 16 Mar | Confirm on-site dates & attendees with Pilot A & B |  | Phase 2
WD14 | Tue 17 Mar | 🔵 C meets Pilot D — 1st personal meeting |  | Phase 2
WD15–16 | Wed–Thu 18–19 Mar | Final refinement only. Logistics confirmed. |  | Phase 2
WD17–18 | Fri–Mon 20–23 Mar | 🟢 ON-SITE commitment meetings: Pilot A then Pilot B |  | Phase 3
WD19–22 | Tue 24 – Fri 27 Mar | Follow-up, LOI close, Day 30 target achieved |  | Phase 3

## How to Use
How to Use This Tracker
GOOGLE SHEETS SETUP (once only)
1. | Upload this file to Google Drive. Right-click → Open with → Google Sheets.
2. | Click Share (top right). Add all four team members. Set to 'Editor'.
3. | Everyone works from the same Google Sheets link — no downloading needed.
DAILY USE
Find your rows | Use the Owner column filter: Data → Create a filter → click the Owner dropdown → select your name.
Update status | Click the Status cell in your row → choose from dropdown: Open / In Progress / Done / Blocked.
Add a deliverable | Paste a shared drive link, SharePoint URL, or file path into the Deliverable Link column.
Add remarks | Type directly in the Remarks column. All changes save automatically and are visible to everyone in real time.
OWNER COLOUR KEY
A (AI / demo) | Green
B (Marketing / commercial) | Amber
C (Pilot relationships) | Purple
D (APQP domain) | Teal
ALL (full team) | Blue
STATUS COLOUR KEY
Open | Grey — not started
In Progress | Yellow — underway
Done | Green — complete · entire row greys out
Blocked | Red — needs team attention
FILTERS
View your tasks only | Data → Create a filter → Owner column → select your name.
View by phase | Filter the WD column: WD1–WD7 = Phase 1, WD8–WD16 = Phase 2, WD17–WD22 = Phase 3.
View blocked tasks | Filter Status column → Blocked.