## Deliverables
Number |  | Project Deliverables expecting by supplier: | DURING | WITHIN | WHO
1 | Native Unigraphics and Team Center capability |  | SOURICNG |  | SUPPLIER
2 | Codesign cost breakdown |  | SOURICNG |  | SUPPLIER
3 | Supplier development team |  | SOURCING |  | SUPPLIER
4 | Components add on to perform all test must be included in the development cost. Stellantis Purch Dept is a reference to require proto piece price to use for the quotation |  | SOURICNG |  | SUPPLIER
5 | Supplier timing releated to vehicle planning. |  | SOURCING |  | SUPPLIER
6 | List of exception (see point 6 TDR) |  | SOURICNG |  | SUPPLIER
7 | Rasi (see point 7 TDR) |  | SOURCING |  | SUPPLIER APPROVAL
8 | During sourcing phase, supplier will have to share CAD data for soft tooling prototype made by CAR MAKER; at the nomination CAD data have to be completely shared by supplier. Anyway the project responsibility is up to supplier according to rasic chart annexed |  | SOURCING |  | SUPPLIER
9 | Complete 2D Drawings |  |  | TKO | SUPPLIER
10 | Supplier has to share the information about his best practices (design, validation and supplier experiences), and discuss and find an agreement with Stellantis Engineering according to the Stellantis Design Integrity process. |  | SOURCING |  | SUPPLIER
11 | Product and process FMEA |  |  | TKO | SUPPLIER
12 | At nomination CAD data have to be completely shared by supplier. Anyway the project responsibility is up to supplier according to rasi chart annexed |  |  | TKO | SUPPLIER
13 | Support car maker on analisys issues related to system performances (example Premature shut off, nozzle compatibility,). |  | DV | PV | SUPPLIER
14 | DV and PV plan must be available to discuss the test proposed (test, quantity of pieces, start/end) |  | SOURCING |  | SUPPLIER
15 | Support for SOP in assembly plant |  |  | SOP | SUPPLIER